## Sheet1
2. Collaborative Structure and Joint Ownership
| Task | Subtasks | Responsible | Due Date | Milestones (Projects)
| 2.1 Create structure to plan and implement the jail transition strategy | 2.11 Create TJC core team | TJC coordinator | Month 1 | • TJC core team and implementation committee meeting regularly, reporting to Jail Transition Council quarterly • TJC org chart created, including roles and responsibilities • Working groups chartered to guide implementation in specific topical areas
|  | 2.12 Convene TJC Implementation Committee | Core team | Month 3
|  | 2.13 Define scope of authority, reporting responsibilities of components of TJC structure | Core team/Jail Transition Council | Month 3
|  | 2.14 Select implementation committee chair or co-chairs | Implementation Committee | Month 3
|  | 2.15 Form topical working groups | Implementation Committee | Month 6
|  | 2.16 Revisit and update committee membership | Implementation Committee | Annually
|  | 2.21 Invite key stakeholders to participate in TJC Implementation Committee | Core team | Month 3
| 2.2 Solidify joint ownership of effort by broad stakeholder community | 2.22 Identify additional partners to bring in based on key roles, knowledge and skills not represented in the current Implementation Committee | Implementation Committee | Annually | • Roster of partners produced • Roster of partners updated every six months as implementation progresses
|  | 2.23 Invite additional partners in | Implementation Committee | Annually
|  | 2.24 Evaluate degree to which jail transition effort is jointly owned and led by jail/criminal justice agencies and the community | Jail Transition Council/Implementation Committee | Annually
| 2.3 Develop information and data-sharing mechanisms | 2.31 Allow partners access to existing data systems, where relevant and appropriate | Each partner agency | Month 9 | • Formal agreements on data access and data-sharing • Case plans, assessment results and other information consistently provided to partners working with the jail transition population
|  | 2.32 Determine distribution for initiative information (assessment results, case plans) | Implementation Committee | Month 6
| 2.4 Create initiative case flow model including all partners | 2.41 Create case flow diagram describing pre-initiative process by which jail population moves through the system and accesses interventions | Core team | Month 4 | • Unified TJC initiative case flow model, including all partners
|  | 2.42 Create TJC case flow diagram indicating the process by which jail population will receive interventions under the TJC systems approach | Core team/Implementation Committee | Month 18